## Sheet1
Task | Start Hours | Hours - Day #1 | Hours - Day #2 | Hours - Day #3 | Hours - Day #4 | Hours - Day #5 | Hours - Day #6 | Total
ProductBacklog | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Requirements | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1
SprintBacklog | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1
GameFoundation | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3
TrelloBoard | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1
VelocityChart | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1
BurndownChart | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Act. Remaining Hours | 9 | 0 | 0 | 0 | 0 | 7 | 2
Est. Remaining Hours | 9.75 | 9 | 0 | 0 | 0 | 0 | 5
Completed Task |  | 0 | 0 | 0 | 0 | 5 | 2
*Formulas Needed